## Foglio1
ID | USER STORY/ACCEPTANCE CRITERIA | TASK | STORY POINTS | OWNER
#1 | As a user I want to have a graphical interface for my drawing application so that I can create drawings on a canvas |  | 1
| GIVEN I have yet to start the application WHEN I run it THEN a graphical interface appears. | Design a GUI for the application following the customer's guidelines |  | Intonti
#2 | As a user I want to have a blank canvas when I start the application so that I can start drawing |  | 2
| GIVEN I open the application WHEN it starts THEN I can only see a blank canvas. | Generate a blank canvas in the GUI |  | Intonti
#3 | As a user I want to have a shape menu with at least a segment line, a rectangular shape and an ellipse shape so that I can customize my drawing |  | 2
| GIVEN I'm using the application WHEN I open the shape menu THEN I can see the shapes that I can draw on the canvas. | Implement a shape menu class |  | Pagano
| GIVEN I'm using the application WHEN I open the shape menu THEN I can see a segment line, a rectangular and an ellipse shape. | Add a segment line shape to the shape menu |  | Pagano
|  | Add a rectangular shape to the shape menu |  | Pagano
|  | Add an ellipse shape to the shape menu |  | Pagano
#4 | As a user I want to select different shapes from a shape menu so that I can choose the shape of my interest |  | 2
| GIVEN I have the shape menu open WHEN I select a shape from the shape menu THEN I can see that shape highlighted in that menu. | Implement an item-menu class |  | Pagano
| GIVEN I have the shape menu open WHEN I select a shape from the shape menu THEN I can see a different pointer so that I know that I selected a shape. | Implement a state pattern for the selection state of the menu items |  | Pagano
|  | Implement pointer changing |  | Pagano
#5 | As a user I want to place a selected shape where i click with the mouse so that I can position it on the canvas |  | 2
| GIVEN I have selected a shape from the shape menu WHEN I left-click on the canvas THEN the shape appears on the canvas with the center of the shape corresponding to the spot I clicked on. | Implement a factory method pattern for the shapes |  | Pagano
#6 | As a user I want to have a color palette fot the border of shapes so that I can customize my drawing |  | 1
| GIVEN I have yet to start the application WHEN I run it THEN I can see a color palette labeled "Border color" | Implement a colour menu and label it "Border Colour" |  | Intonti
#7 | As a user I want to have a color palette fot the border of shapes so that I can customize my drawing |  | 1
| GIVEN I have yet to start the application WHEN I run it THEN I can see a color palette labeled "Interior color" | Implement a colour menu and label it "Interior Colour" |  | Intonti
#8 | As a user I want to have two colour palettes with at least 8 colours for the border and the interior of shapes so that I can customize my drawing |  | 1
| GIVEN I'm using the application WHEN I open the border color palette THEN I can see at least 8 colours in the palette | Implement the following items for the border colour palette: red, green, blue, yellow, purple, orange, black and white |  | Memoli
| GIVEN I'm using the application WHEN I open the interior color palette THEN I can see at least 8 colours in the palette | Implement the following items for the interior colour palette: red, green, blue, yellow, purple, orange, black and white |  | Memoli
GIVEN I'm using the application WHEN I select a colour from the border palette THEN I can see it highlighted in the border color palette
GIVEN I'm using the application WHEN I select a colour from the interior palette THEN I can see it highlighted in the interior color palette
#9 | As a user I want to choose a colour from the border palette so that i can change the colour of the shape border before I position the shape on the canvas |  | 1
| GIVEN I have selected a colour from the border palette AND I've selected a shape from the shape menu WHEN I position it on the canvas THEN the shape border will be of the selected colour. | implement a border colour changing method for inserting shapes |  | Memoli
GIVEN I'm using the application WHEN I select a colour from the border palette THEN I can see it highlighted in that menu.
#10 | As a user I want to choose a colour from the interior palette so that I can change the colour of the shape interior before I position the shape on the canvas |  | 1
| GIVEN I have selected a colour from the interior palette AND I've selected a shape from the shape menu WHEN I position it on the canvas THEN the shape interior will be of the selected colour. | Implement an interior colour changing method for inserting shapes |  | Memoli
GIVEN I'm using the application WHEN I select a colour from the interior palette THEN I can see it highlighted in that menu.
#11 | As a user I want to have a menu bar so that I can import/export drawings |  | 1
| GIVEN I have yet to start the application WHEN I run it THEN the interface includes a menu bar on top of the GUI with a "File" option. | Design a menu-bar with Load/Save option |  | Squitieri
GIVEN I am using the application WHEN I click on the "File" option of the menu bar THEN two options named "Save" and "Load" appear.
#12 | As a user I want to save the drawing on a file so that I can modify it later |  | 2
| GIVEN I'm using the application WHEN I select the "Save" button AND type a name for the drawing THEN I save it on the file system. | Implement a save on file method |  | Squitieri
#13 | As a user I want to load a saved drawing so that i can modify it later |  | 3
| GIVEN I'm using the application WHEN I select the "Load" button AND select a previously saved drawing THEN I can see it on the canvas. | Implement a load on file method |  | Squitieri
#14 | As a user I want to select one or more shapes on the canvas so that I can delete, resize, cut, copy and recolour the selected shape(s) |  | 2
| GIVEN I'm using the application WHEN I left-click on a shape on the canvas THEN I can see a bounding appear around the selected shape. | Implement a selection state method |  | Memoli
GIVEN I'm using the application WHEN I left-click on one or more shapes on the canvas while pressing CTRL THEN I can see bounding boxes appear around the selected shapes.
#15 | As a user I want to choose a colour from the border palette while a shape on the canvas is selected so that I can change the colour of its border |  | 1
| GIVEN I have a shape selected on the canvas WHEN I select a colour from the border palette THEN I can modify the colour of its border. | implement a border colour changing method for selected shapes on the canvas |  | Memoli
#16 | As a user I want to choose a colour from the interior palette while a shape on the canvas is selected so that I can change the colour of its interior |  | 1
| GIVEN I have a shape selected on the canvas WHEN I select a colour from the interior palette THEN I can modify the colour of its interior. | implement a interior colour changing method for selected shapes on the canvas |  | Memoli
#30 | As a user I want to have a canvas larger than the board size so that I can have a big drawing area |  | 2
| GIVEN I'm using the application WHEN I open a drawing THEN I can see bars through which i can access other areas of the drawing | Insert a pane larger than the board size |  | Intonti
GIVEN I'm using the application WHEN I scroll down with the mouse wheel on the canvas THEN I can move in another area of the canvas positioned below the current one
GIVEN I'm using the application WHEN I scroll up with the bar positioned to the left of the canvas THEN I can move in another area of the canvas positioned above the current one
GIVEN I'm using the application WHEN I scroll right with the bar positioned to the bottom of the canvas THEN I can move in another area of the canvas positioned at the right of the current one
GIVEN I'm using the application WHEN I scroll left with the bar positioned to the bottom of the canvas THEN I can move in another area of the canvas positioned at the left of the current one
#31 | As a user I want to scroll on the canvas so that I can access the area of my interest |  | 3
| GIVEN I'm using the application WHEN I scroll up with the mouse wheel on the canvas THEN I can move in another area of the canvas positioned above the current one | Insert a scroll pane in the interface |  | Intonti
GIVEN I'm using the application WHEN I select the grid size AND enter a positive desired value THEN I can change the size of the enabled grid
|  | TOTAL | 29