## Foglio1
ID | USER STORY/ACCEPTANCE CRITERIA | TASK | STORY POINTS | OWNER
17 | As a user I want to have a context menu associated with the canvas so that I can paste a shape |  | 1
| GIVEN I have copied or cut a shape WHEN I right-click on the canvas THEN a context menu containing the "Paste" option will appear | Implement a context menu for the canvas with the "Paste" option |  | Intonti
18 | As a user I want to have a context menu associated with selected shape(s) on the canvas so that I can delete, cut, copy, paste and move the associated shape to the front or the back of the drawing |  | 1
| GIVEN I'm using the application WHEN I right-click on the selected shape(s) on the canvas THEN a context menu containing the "Delete", "Cut", "Copy", "Paste", "Send to front", "Send forward", "Send to back" and "Send backward" options will appear | Implement a context menu for shapes with the "Delete", "Cut", "Copy", "Paste", "Send to front", "Send forward", "Send to back" and "Send backward" options |  | Intonti
19 | As a user I want to delete a shape on the canvas so that I can adjust my drawing |  | 2
| GIVEN I selected a shape on the canvas WHEN I select the "Delete" option on the context menu of that shape THEN I remove the shape from the canvas | Implement delete shape functionality |  | Squitieri
20 | As a user I want to move a shape on the canvas so that I can adjust my drawing |  | 5
| GIVEN I selected a shape on the canvasd WHEN I drag the mouse THEN I can move the shape in the position of the canvas where i drop the mouse | Implement drag shape functionality |  | Intonti
21 | As a user I want to change the size of a shape on the canvas so that I can adjust my drawing |  | 5
| GIVEN I selected a shape on the canvas WHEN I drag the mouse starting from the vertex of its bounding box THEN I can resize the shape according to where I drop the mouse | Implement resize shape functionality |  | Squitieri
22 | As a user I want to copy a shape on the canvas so that I can save it and use it later |  | 2
| GIVEN I selected a shape on the canvas WHEN I select the "Copy" option on the context menu of the shape THEN I can save it for later paste operations | Implement copy shape functionality |  | Memoli
23 | As a user I want to cut a shape on the canvas so that I can save it and adjust my drawing |  | 3
| GIVEN I selected a shape on the canvas WHEN I select the "Cut" option on the context menu of the shape THEN I can save it for later paste operations AND I remove it from the canvas | Implement cut shape functionality |  | Memoli
24 | As a user I want to paste a previously copied or cut shape on the canvas so that I can adjust my drawing |  | 2
| GIVEN I'm using the application WHEN I select the "Paste" option on the context menu of the canvas or the context menu of a selected shape on the canvas THEN I can position a previously saved shape to the canvas where i opened the context menu | Implement paste shape functionality |  | Memoli
26 | As a user I want to send a shape on the canvas to the front of the drawing area so that I can modify the visibility compared to other shapes |  | 3
| GIVEN I'm using the application WHEN I select "Send forward" button on the context menu of a selected shape on the canvas THEN I can move the shape ahead the one that is immediately over it | Implement move shape up by one layer functionality |  | Pagano
| GIVEN I'm using the application WHEN I select "Send to front" button on the context menu of a selected shape on the canvas THEN I can move the shape ahead of all the shapes | Implement move shape to the front layer functionality |  | Pagano
27 | As a user I want to send a shape on the canvas to the back of the drawing area so that I can modify the visibility compared to other shapes |  | 3
| GIVEN I'm using the application WHEN I select "Send backward" button on the context menu of a selected shape on the canvas THEN I can move the shape behind the one that is immediately under it | Implement move shape down by one layer functionality |  | Pagano
| GIVEN I'm using the application WHEN I select "Send to back" button on the context menu of a selected shape on the canvas THEN I can move the shape behind all the shapes | Implement move shape to the back layer functionality |  | Pagano
25 | As a user I want to cancel previous operations as far as the first one so that I can fix mistakes |  | 5
| GIVEN I'm using the application WHEN I select "Undo" button THEN I can delete the last operation and restore the previous state of the drawing | Implement undo method in the command class |  | Memoli
45 | As a user I want to click on the canvas while one or more shapes on the canvas is selected so that I can deselect the shapes on the canvas |  | 2
| GIVEN I have one or more shapes selected on the canvas WHEN I left-click on an empty spot the canvas THEN I can see the boxes around the selected shapes no more. | Implement listener method of click on an empty spot of the canvas |  | Intonti
GIVEN I have one or more shapes selected on the canvas WHEN I left-click on a selected shape on the canvas while holding CTRL THEN I can see the boxes around the shape on which I clicked no more.
|  | TOTAL | 34