## Foglio1
ID | USER STORY/ACCEPTANCE CRITERIA | TASK | STORY POINTS | OWNER
28 | As a user I want to have a "Zoom" slider with at least 8 different zoom levels so that I can zoom in and out of the drawing |  | 2
| GIVEN I have yet to start the application WHEN I run it THEN I can see a "Zoom" slider below the canvas with 8 levels labeled with percentages from 0 to 200 | Implement a slider labeled "Zoom" on the interface |  | Federico Memoli
29 | As a user I want to zoom in and zoom out on the canvas so that I can orient myself on the drawing |  | 3
| GIVEN I'm using the application WHEN I drag the "Zoom" slider on the right THEN I can have a closer look at the drawing seeing bigger the shapes AND seeing a smaller area of the canvas | Implement a listener method that binds the zoom level with the "Zoom" slider position |  | Federico Memoli
| GIVEN I'm using the application WHEN I drag the "Zoom" slider on the left THEN I can have a wide look at the drawing seeing smaller the shapes AND seeing a bigger area of the canvas |  |  | Federico Memoli
32 | As a user I want to have a "Grid on/off" check box so that I can choose wheter to have a grid on the canvas visible or not |  | 1
| GIVEN I have yet to start the application WHEN I run it THEN I can see a "Grid on/off" check box | Implement a check box labeled "Grid on/off" on the interface |  | Beniamino Squitieri
33 | As a user I want to have a "Grid size" slider so that I can choose the size of the squares of the grid on the canvas. |  | 1
| GIVEN I have yet to start the application WHEN I run it THEN I can see a slider labeled "Grid size" | Implement a slider labeled "Grid size" on the interface |  | Beniamino Squitieri
34 | As a user I want to enable a grid of a chosen size so that I can better position the shapes on the canvas |  | 1
| GIVEN I am using the application WHEN I click on the "Grid on/off" check box while the check box is not selected THEN I can see a grid on the canvas with a square size proportional to the one defined with the "Grid size" slider | Implement a listener method that binds the visibility of the grid with the "Grid on/off" check box |  | Beniamino Squitieri
| GIVEN I am using the application WHEN I click on the "Grid on/off" check box while the check box is selected THEN I can no longer see a grid on the canvas |  |  | Beniamino Squitieri
35 | As a user I want to drag my mouse on the "Grid size" slider so that I can change the square size of the grid on the canvas. |  | 3
| GIVEN I am using the application WHEN I drag my mouse on the "Grid size" slider while the "Grid on/off" check box is selected THEN I can see a grid on the canvas with a square size proportional to the one defined with the "Grid size" slider | Implement a listener method that binds the grid square size with the slider position |  | Beniamino Squitieri
36 | As a user I want to have a text menu with a text field and a combo box so that I can cusomize my drawing |  | 1
| GIVEN I have yet to start the application WHEN I run it THEN I can see a text menu with a text field and a combo box | Implement an area containing a text field and a combo box on the interface |  | Beniamino Squitieri
37 | As a user I want to have a "Content" text field in the text menu so that I can customize my drawing |  | 1
| GIVEN I am using the application WHEN I open the text menu THEN I can see a text field with "Content" as the prompt text in the text menu | Implement a text field with "Content" as its prompt text on the interface |  | Beniamino Squitieri
38 | As a user I want to have a "Size" combo box in the text menu so that I can define the character size of the content of the labels created through the context menu |  | 1
| GIVEN I am using the application WHEN I open the text menu THEN I can see a combo box labeled "Size" containing 20 options labeled as numbers from 10 to 100 in the text menu. | Implement a combo box labeled "Size" in the "text menu" area |  | Beniamino Squitieri
39 | As a user I want to press ENTER on the "Content" text field while the text field is not empty so that I can insert a text containing th estring I wrote in the text field with the size that is selected in the "Size" combo box at the center of my canvas. |  | 3
| GIVEN I am using the application WHEN I press ENTER while the "Content" text field is not empty THEN a label containing the text that is written in the "Content" text field with the character size that is selected in the "Size" combo box appears | Implement a method on the commit of the "Content" text field that spawns the label on the canvas |  | Adolfo Pagano
40 | As a user I want to click one of the options of the "Size" combo box while no labels on the canvas are selected so that I can define the character size of the next label I will insert on the canvas. |  | 1
| GIVEN I am using the application WHEN I click on one of the options of the "Size" combo box while no labels on the canvas are selected THEN I can see the selected option occupy the area of the combo box | Implement a method that triggers upon clicking one of the "Size" combo box items so that it changes the character size of the upcoming label |  | Adolfo Pagano
41 | As a user I want to click on one of the options of the "Size" combo box while one or more labels on the canvas are selected so that I can change the character size of the selected labels |  | 3
| GIVEN I am using the application WHEN I click on one of the options of the "Size" combo box while one or more labels on the canvas is selected THEN I can see the character size of the content of the selected labels become the number selected in the "Size" combo box | Implement a method that triggers upon clicking one of the "Size" combo box items so that it changes the character size of the selected labels |  | Adolfo Pagano
42 | As a user I want to have "Rotate by 90 degrees clockwise" and "Rotate by 90 degrees counter-clockwise" options close to the shape menu so that I can precisely rotate selected shapes on the canvas |  | 1
| GIVEN I am using the application WHEN I open the shape menu THEN I can see the "Rotate by 90 degrees clockwise" and "Rotate by 90 degrees counter-clockwise" options close to the shape menu | Implement 2 buttons labeled as "Rotate by 90 degrees clockwise" and "Rotate by 90 degrees counter-clockwise" on the interface |  | Giovanni Intonti
43 | As a user I want to rotate the selected shapes on the canvas by using the mouse wheel so that I can customize my drawing |  | 5
| GIVEN I have one or more shapes selected on the canvas WHEN I scroll my mouse wheel while holding CTRL THEN I can see the shapes rotating by a number of degrees equal to the angle of my dragging | Implement a listener method that triggers on selected shapes when scrolling while holding CTRL |  | Giovanni Intonti
44 | As a user I want rotate the selected shapes on the canvas by clicking a "Rotate" option on the shape menu so that I can customize my drawing |  | 3
| GIVEN I have one or more shapes selected on the canvas WHEN I click a "Rotate by 90 degrees clockwise" option THEN I can see the shapes rotated clockwise by 90 degrees | Implement a method that triggers upon clicking the "Rotate by 90 degrees clockwise" button |  | Giovanni Intonti
| GIVEN I have one or more shapes selected on the canvas WHEN I click a "Rotate by 90 degrees counter-clockwise" option THEN I can see the shapes rotated counter-clockwise by 90 degrees | Implement a method that triggers upon clicking the "Rotate by 90 degrees counter-clockwise" button |  | Giovanni Intonti
46 | As a user I want to move a selected label on the canvas |  | 1
| GIVEN I'm using the application WHEN I left-click on a label on the canvas THEN I can see a bounding box appear around the selected label. | Implement selection functionality for one o more labels. |  | Adolfo Pagano
GIVEN I'm using the application WHEN I left-click on one or more labels on the canvas while pressing CTRL THEN I can see bounding boxes appear around the selected labels.
47 | As a user I want to select one or more labels on the canvas so thatI can move, delete, cut, copy, paste, send to the front or to the back of the drawing them, change their font size |  | 3
| GIVEN I selected a shape on the canvas WHEN I drag the mouse THEN I can move the selected label in the position of the canvas where i drop the mouse | Implement drag functionality for selected labels |  | Adolfo Pagano
46 | As a user I want to move a selected label on the canvas |  | 1
| GIVEN I'm using the application WHEN I left-click on a label on the canvas THEN I can see a bounding box appear around the selected label. | Implement selection functionality for one o more labels. |  | Adolfo Pagano
GIVEN I'm using the application WHEN I left-click on one or more labels on the canvas while pressing CTRL THEN I can see bounding boxes appear around the selected labels.
47 | As a user I want to select one or more labels on the canvas so thatI can move, delete, cut, copy, paste, send to the front or to the back of the drawing them, change their font size |  | 3
| GIVEN I selected a shape on the canvas WHEN I drag the mouse THEN I can move the selected label in the position of the canvas where i drop the mouse | Implement drag functionality for selected labels |  | Adolfo Pagano
| GIVEN I'm using the application WHEN I right-click on the selected label(s) on the canvas THEN a context menu containing the "Delete", "Cut", "Copy", "Paste", "Send to front", "Send forward", "Send to back" and "Send backward" options will appear |  |  | Adolfo Pagano
| GIVEN I selected a label on the canvas WHEN I select the "Delete" option on the context menu of that label THEN I remove the label from the canvas | Update the already existing delete method. |  | Adolfo Pagano
| GIVEN I selected a label on the canvas WHEN I select the "Copy" option on the context menu of the label THEN I can save it for later paste operations | Update the alreadyexixsting copy method. |  | Adolfo Pagano
| GIVEN I selected a label on the canvas WHEN I select the "Cut" option on the context menu of the label THEN I can save it for later paste operations AND I remove it from the canvas | Update the already existing cut method. |  | Adolfo Pagano
| GIVEN I'm using the application WHEN I select the "Paste" option on the context menu of the canvas or the context menu of a selected label on the canvas THEN I can position a previously saved label to the canvas where I opened the context menu | Update the already existing paste method. |  | Adolfo Pagano
| GIVEN I'm using the application WHEN I select "Send forward" button on the context menu of a selected label on the canvas THEN I can move the label ahead the one that is immediately over it | Update the alreadyexisting Send Forward method. |  | Adolfo Pagano
| GIVEN I'm using the application WHEN I select "Send to front" button on the context menu of a selected label on the canvas THEN I can move the label ahead of all the labels and shapes | Update the already existing Send to Front method. |  | Adolfo Pagano
| GIVEN I'm using the application WHEN I select "Send backward" button on the context menu of a selected label on the canvas THEN I can move the label behind the one that is immediately under it | Update the already existing Send backward method. |  | Adolfo Pagano
| GIVEN I'm using the application WHEN I select "Send to back" button on the context menu of a selected label on the canvas THEN I can move the label behind all the shapes and labels | Update the already existing Send to back method. |  | Adolfo Pagano
|  | TOTAL | 34